| OCT EAST "FLOOD AT MANDRILL MOUNTAIN" |  |
| --- | --- |
| Description | Duration |
| Signed Contract 签订合同 | 06/06/2008 |
| First Payment Received from OCT EAST 首付款 | 06/20/2008 |
| Revised Plot Plans 修改后的平面图 | 06/20/2008-06/30/2008 |
| Theme Drawings of New Set Pieces 场地包装图 | 06/20/2008-07/01/2008` |
| US & Local Equipment Manufacturing Starts美国和当地设备开始采购 | 06/20/2008 |
| Contract All Staff 合同员工到位 | 06/20/2008 |
| Rehearsal Script First Draft 排练剧本初稿 | 06/20/2008-07/01/2008 |
| Rehearsal Script Final Draft (Approval) 排练最终剧本 | 08/01/2008 |
| Music & Sound Effect 音乐制作 | 07/15/2008-08/15/2008 |
| US Made Equipment Shipping from US Port | 07/07/2008-07/15/2008 |
| US Made Equip Shipment arriving at port美国设备到港 | 08/01/2008-08/15/2008 |
| Chinese Made Equip Arriving at Park中国设备到达公园 | 08/01/2008 |
| Installation Special Effects Equipment 安装设备 | 08/02/2008-08/31/2008 |
| Installation of Stunt and Specialized Equipment特技设备安装 | 08/02/2008-08/31/2008 |
| Computer Program Show Time Coding Adjustment 控制系统调试 | 08/20/2008-09/20/2008 |
| Set Construction Completetion (OCT EAST) 场地施工完成 | 08/01/2008 |
| OCT EAST Special Effects Install and Completion 东部华侨城特效安装完成 | 07/10/2008-08/01/2008 |
| Install of Additional Piping / Hoses / Electrical Wiring.额外管线完成 | 07/1/2008 |
| All Pulling of Wires through Conduit (OCT EAST)牵线 | 07/15/2008 |
| Testing / Training of SFX Equipment 特效调试 | 08/24/2008-08/31/2008 |
| Rehearsal Schedule 排练日程 | 08/01/2008-09/14/2008 |
| Show Opening 开业 | 09/15/2008 |